## Sheet1
BTN UPDATE & ROLLOUT PLAN
Group | On Master | Action Item | Notes | Due Date | Owner | Support Team | Status
|  | Create new BTN look/feel | Complete & Debra approved on 4.20.15 | n/a | Casey | Mich, DD, AD | Complete
|  | Create BTN deck slides, with approved look/feel |  | 4.24.15 | Casey | Mich, DD, AD
|  | Announcement to employees about slide | 1) Casey to: a) Send note to Beth, Tony, EB, Clint & Mike (others?) about using in presentations b) Present at S+M call c) Attend Beth's staff meeting | Note - 4.24.15 Meetings - when held | Casey
|  | Casey & Sam meet to discuss other figures and how/where we can use them on our website |  | 5.1.15 | Casey | Sam
|  | Web property updates to look/feel | All Web Properties - Banners only a) www.cds-global.com b) www.cdsglobal.ca c) www.cdsglobal.co.uk | 5.1.15 | Casey | Mich, Sam, DD, AD
|  | Updates to content | 1) Marketing Assets a) Data Sheets b) Decks c) Case Studies | 5.8.15 | Casey | Will, DD, AD
|  | Social Asset updates to look/feel | All social properties - US & Global a) LinkedIn b) Twitter - CDSG, CDSG NP & CDSG UK c) FB d)any others? | 5.15.15 | Casey | Mich, Sam, DD, AD
|  | Updates to Marketing Banners | Update NP booth banner to new numbers, Laura to work with Nick. LR - Please have Emmy sign off before going to print. | 6.1.15 | Casey | Laura, Nick, Emmy
|  | Brand book | All pages to be updated/created: a) All webpage examples b) Events c) Add POV/Solution Wheel d) Any other? | 6.5.15 | Casey | Mich, DD, Will, AD
|  | Casey email to company about these updates | **Need to run by DJ first, but will plan to send a note regarding the work, changes, binder pages, etc | 6.12.15 | Casey | DD, Jamey, AD, Will
|  | BTN Video | Last to be completed | 6.30.15 | Casey | Nick, DD, Will